## Project Plan
No. | Milestone | Project Tasks | Responsibility | FA Team | Estimated Delivery By End of Week | Actual Delivery | Status | Comments | WEEK
[9 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | CONTRACTS | Contract Signed | Client |  | 0 |  | Incomplete
|  | . | . |  | .
2 | Environment Creation | New Environment Request | Funds-Axis |  | 1 |  | Incomplete
|  | New Environment Created | Funds-Axis | Tech | 2 |  | Incomplete
|  | New Environment Review | Funds-Axis | Projects | 2 |  | Incomplete
|  | . |  |  |  |  | .
3 | Portfolio SETUP | Portfolio & Organisational Structure Information Provided to Funds-Axis | Client |  | 2 |  | Incomplete
|  | Portfolio & Organisational Structure Set-up | Funds-Axis | Projects | 3 |  | Incomplete
|  | . |  |  |  |  | .
4 | PROSPECTUS RULES | Prospectus Rules Matrix Provided to Funds-Axis | Client |  | 3 |  | Incomplete
|  | Prospectus Rules Set-up | Funds-Axis | Rules Team |  |  | Incomplete
5 | MARKET DATA SETUP | Market Data Feed Received | Client |  | 0 (assuming ICE) |  | Incomplete
|  | Market Data Provider Set-up | Funds-Axis | EDM | 1 (assuming ICE) |  | Incomplete
|  | . | . |  |  |  | .
6 | Holdings Data SETUP | Holdings Data Feed Provided to Funds-Axis | Client |  | 2 |  | Incomplete
|  | Holdings Data Mapping Set-up | Funds-Axis | EDM | 4 |  | Incomplete
|  | Holdings Uploads & Reconciliation | Funds-Axis | Projects | 6 |  | Incomplete
|  | . | . |  |  |  | .
7 | AUTOMATION | Client FTP Set-up | Funds-Axis | EDM | 3 |  | Incomplete
|  | Uploads Procedure | Funds-Axis | EDM | 3 |  | Incomplete
|  | EasyMorph Set-up | Funds-Axis | EDM | 5 |  | Incomplete
|  | New security - market data request automation | Funds-Axis | EDM | 6 |  | Incomplete
|  | Upload Automation | Funds-Axis | EDM | 5 |  | Incomplete
8 | HIGHWIRE SETUP | HighWire Set-up | Funds-Axis | Projects |  |  | Incomplete
|  | . | .
9 | DATA QUALITY | CIS / Asset Eligibility Research (starts as sonnas holdings received) | Funds-Axis | Asset Eligibility | 6 |  | Incomplete
|  | HighWire Data Quality Review - Derivatives |  | Risk Team |  |  | Incomplete
|  | HighWire Data Quality Review - Other | Funds-Axis | Platform Mgmt | 8 |  | Incomplete
|  | . | . | [6 empty] | . |  |  | . | bar: 7; 10; 13; 16
10 | REGULATORY RULES | Regulatory Rules - Specification and Test Documentation | Funds-Axis | Rules Team |  |  | Incomplete
|  | Regulatory Rules - Breach Review | Funds-Axis | Projects Team |  |  | Incomplete
.
11 | BAU HANDOVER | Handover to Funds-Axis BAU Team | Funds-Axis | Projects / BAU |  |  | Incomplete
|  | . | .
12 | Client Sign-Off | Regulatory Rules Testing & Documentation (on demo environment) | Client | Rules Team |  |  | Incomplete | bar: 7 to 10
|  | Client Onboarding | Client | Projects Team |  |  | Incomplete | bar: 7 to 10
|  | Client Training | Client | Projects Team |  |  | Incomplete | bar: 7 to 10
|  | Client Testing and sign-off - all except Prospectus Rules | Client | Projects Team |  |  | Incomplete | bar: 7 to 10
|  | Edge Issues | Funds-Axis |  |  |  | Incomplete
|  | Client Sign-off - Prospectus Rules | Client | Projects Team |  |  | Incomplete
.